### Incident Status Summary (ICS-209)

| 1: Date 05/19/2013 | 2: Time 1600 | 3: Initial ¦ Update ¦ Final ¦ ¦ XX | 4: Incident Number MN-MNS-161-007 | 5: Incident Name Green Valley Fire |
| --- | --- | --- | --- | --- |

| 6: Incident Kind Wildfire (Full Suppression) | 7: Start Date Time 05/14/2013 1530 | 8: Cause Under Investigation | 9: Incident Commander Mike Aultman | 10: Incident Command Organization Type 2 Team | 11: State-Unit MN-MNS |
| --- | --- | --- | --- | --- | --- |

| 12: County Becker | 13: Latitude and Longitude Lat: 46° 49´ 40" Long: 95° 11´ 4" Ownership: MN-MNS | 14: Short Location Description (in reference to nearest town): 7 miles NW of Menahga MN |
| --- | --- | --- |

| 15: Size/Area Involved 7,100 ACRES | 16: % Contained or MMA 100 Percent | 17: Expected Containment Date: 05/19/2013 | 18: Line to Build 0 Miles | 19: Estimated Costs to Date $1,125,000 | 20: Declared Controlled Date: Time: |
| --- | --- | --- | --- | --- | --- |

| 21: Injuries this Reporting Period: | 22: Injuries to Date: | 23: Fatalities | 24: Structure Information |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 0 | 0 | 0 | Type of Structure | # Threatened | # Damaged | # Destroyed |
| 25: Threat to Human Life/Safety: Evacuation(s) in progress ---- No evacuation(s) imminent -- Potential future threat -------- No likely threat --------------- XX |  |  | Residence |  | 2 | 12 |
|  |  |  | Commercial Property |  |  | 3 |
|  |  |  | Outbuilding/Other |  | 6 | 43 |

26: Projected incident movement/spread 12, 24, 48, and 72 hour time frames: 12 hours: No spread is anticipated. Fire is contained. 24 hours: No spread is anticipated. Fire is contained. 48 hours: No spread is anticipated. Fire is contained. 72 hours: No spread is anticipated. Fire is contained.

27: Values at Risk: include communities, critical infrastructure, natural and cultural resources in 12, 24, 48 and 72 hour time frames: 12 hours: None. 24 hours: None. 48 hours: None. 72 hours: None.

28: Critical Resource Needs (amount, type, kind and number of operational periods () in priority order in 12, 24, 48, and 72 hour time frames): 12 hours: None. 24 hours: None. 48 hours: None. 72 hours: None.

29: Major problems and concerns (control problems, social/political/economic concerns or impacts, etc.) Relate critical resources needs identified above to the Incident Action Plan. Thunderstorms and heavy precipitation are forecasted.

| 30: Observed Weather for Current Operational Period Peak Gusts (mph): 12 Max. Temperature: 70 Wind Direction: E Min. Relative Humidity: 70 | 31: Fuels/Materials Involved: 3 Tall Grass (2.5 Feet) Mature jack pine, red pine plantations, hardwoods, agricultural fields and swamp grass. |
| --- | --- |

32: Today's observed fire behavior (leave blank for non-fire events): Smoldering in heavy fuels and exposed peat.

33: Significant events today (closures, evacuations, significant progress made, etc.): All out of area line resources have been demobed. The fire will be turned over to the Park Rapids Area DNR at 1900 today.

| 34: Forecasted Weather for next Operational Period Wind Speed (mph): 15 Temperature: 67 Wind Direction: NE Relative Humidity: 69 | 35: Estimated Control Date and Time: | 36: Projected Final Size: 7100 Acres | 37: Estimated Final Cost: |
| --- | --- | --- | --- |

38: Actions planned for next operational period: Fire will be staffed by the Park Rapids Area DNR.

39: For fire incidents, describe resistance to control in terms of:

1. Growth Potential - Low

2. Difficulty of Terrain - Medium

40: Given the current constraints, when will the chosen management strategy succeed? The fire is contained.

41: Projected demobilization start date: 05/18/2013 0900

42: Remarks: The one additional commercial structure destroyed during the initial burning period was a sawmill discovered in a more thorough assessment. Additional precipitation was received with significant precipitation in the forecast. Fifty three local fire departments have assisted with the fire suppression efforts.

43: Committed Resources (Supplemental Committed Resources follow the first block)

| Agency | CRW1 |  | CRW2 |  | HEL1 | HEL2 | HEL3 | ENGS |  | DOZR |  | WTDR | OVHD | Camp Crews | Total Personnel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | SR | ST | SR | ST | SR | SR | SR | SR | ST | SR | ST | SR | SR |  |  |
| USFS | 0 |  |  |  |  |  |  |  |  |  |  |  | 3 |  | 3 |
| BIA |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  | 1 |
| FWS |  |  |  |  |  |  |  |  |  |  |  |  | 2 |  | 2 |
| LGR |  |  |  |  |  |  |  |  |  |  |  |  | 3 |  | 3 |
| ST |  |  |  |  |  |  |  | 2 |  |  |  |  | 15 |  | 19 |
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 24 | 0 | 28 |

| Total personnel by agency are listed in the first section of committed resources. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Agency | C215 | C415 | BMDR | TPL1 | TPL2 | TPL3 | TPL4 | VANS |
|  | SR | SR | SR | SR | SR | SR | SR | SR |
| USFS |  |  |  |  |  |  |  |  |
| BIA |  |  |  |  |  |  |  |  |
| FWS |  |  |  |  |  |  |  |  |
| LGR |  |  |  |  |  |  |  |  |
| ST |  |  |  |  |  |  |  |  |
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

44: Cooperating and Assisting Agencies Not Listed Above: Menahga Fire Department assisted with today's suppression efforts.

| 45: Prepared by: Robert Heisel SITL | 46: Approved by: Michael Aultman ICT2 | 47: Sent to:EACC by: R Heisel Date: 05/19/2013 Time: 1600 |
| --- | --- | --- |